## LPPP1
SIKEDIPP High Level Timeline
Date: | 2022-05-13 | 2022-05-13
Task Name | Planned Start Date | Tanggal Mulai | Planned End Date | Tanggal Selesai | Status | Progress | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  |  | Jun-22
[7 empty] | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-06-03 | 2022-06-10 | 2022-06-17
[7 empty] | WEEK 0 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11
SIKEDIPP Project | 2022-11-04 | 2022-04-11 | 31/5/2022 | 2022-05-31 | On-Track | 64.53%
Project Kick-Off | 2022-11-04 | 2022-04-11 | 2022-11-04 | 2022-04-11 | Selesai | 100%
Desain Aplikasi & SKPL |  | 2022-04-11 |  | 2022-04-16 | Selesai | 100%
Pengaturan Lingkungan Development |  | 2022-04-17 |  | 2022-04-21 | Selesai | 100%
Pengaturan Platform Laravel |  | 2022-04-17 |  | 2022-04-21 |  | 100%
Pengaturan Database |  | 2022-04-17 |  | 2022-04-21 |  | 100%
Pengembangan Aplikasi |  | 2022-04-22 |  | 2022-05-22 | On-Track | 78%
Pengembangan Halaman Login |  | 2022-04-22 |  | 2022-04-25 | Selesai | 100%
Pengembangan Halaman Administrator |  | 2022-04-26 |  | 2022-05-09 | Selesai | 100%
Libur Lebaran |  | 2022-04-29 |  | 2022-05-08 | Selesai | 100%
Pengembangan Halaman Pegawai |  | 2022-05-10 |  | 2022-05-15 | On-Track | 60%
Pengembangan Halaman Atasan Pegawai |  | 2022-05-17 |  | 2022-05-22 | On-Track | 30%
Development Testing |  | 2022-05-24 |  | 2022-05-26 |  | 0%
Materi Training dan Dokumentasi |  | 2022-05-24 |  | 2022-05-26 |  | 0%
User Training |  | 2022-05-27 |  | 2022-05-28 |  | 0%
User Acceptance Test |  | 2022-05-30 |  | 2022-05-31 |  | 0%
Keterangan
| Minggu Laporan | Minggu Laporan
| Libur Lebaran | Libur Lebaran
Formulas:
Tanggal Mulai = [Tanggal Mulai, row above]
Tanggal Mulai = [Tanggal Selesai, row above]
Tanggal Selesai = [Tanggal Mulai]
Tanggal Selesai = [Tanggal Mulai]+5

## DND
No. | Activity | Planned Duration (days) | Actual/Estimated Duration (days)
1 | Project Kick-Off | 1 | 1
2 | Architecture and Solution Design | 8 | 21
3 | Joint Specification | 2 | 39
4 | Data Tapping and Sensor Retrofitting | 56 | 56
5 | Development | 76 | 59
6 | Development Testing | 3 | 3
7 | Server, Gateway, Platform, and Database Setup | 10 | 20
8 | Training Material and Documentation | 3 | 3
9 | User Training | 1 | 1
10 | User Acceptance Test | 2 | 2
11 | Go Live Support | 3 | 3
12 | ThingWorx Foundation Developer Training | 4 | 4

## LPPP1B op1
Collins Aerospace Indonesia Lighthouse Pilot Project Phase 1B 10 Assets High-Level Timeline V1.0
| Date: |  | 2022-05-13
| Task Name | Planned Start Date | Estimated Start Date | Planned End Date | Estimated End Date | Status | Progress | 2022-05-01 |  |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  | 2022-06-01
[8 empty] | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12
[8 empty] | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 16 | WEEK 16 | WEEK 17 | WEEK 18 | WEEK 19 | WEEK 20 | WEEK 21 | WEEK 22 | WEEK 23 | WEEK 24 | WEEK 25 | WEEK 26 | WEEK 27 | WEEK 28 | WEEK 29 | WEEK 30 | WEEK 31 | WEEK 32 | WEEK 33
| Lighthouse Pilot Project Phase 1 10 Assets | 2021-11-03 | 2022-05-02 | 2022-03-24 | 2022-07-27 | Will be Late | 37.28%
| Project Kick-Off | 2021-11-03 | 2022-05-02 | 2021-11-03 | 2022-05-02 | On-Track | 100%
| Architecture and Solution Design | 2021-11-04 | 2022-05-03 | 2021-11-15 | 2022-05-05 | Late | 100%
| Joint Specification | 2021-11-16 | 2022-05-06 | 2021-11-17 | 2022-05-06 | Late | 100%
| Data Tapping | 2021-11-17 | 2022-05-09 | 2022-02-01 | 2022-07-15 | Will be Late | 25%
| Controller Direct Data Tapping |  | 2022-01-27 |  | 2022-02-27 |  | 20%
| Sensor Retrofitting | [5 empty] | 30%
| Development | 2021-11-16 | 2021-12-14 | 2022-03-01 | 2022-03-25 | Will be Late | 83.33%
| Project Baseline Development |  | 2021-12-14 |  | 2022-01-06 |  | 100%
| Database Development |  | 2022-01-03 |  | 2022-01-14 |  | 85%
| ThingWorx Work Packages |  | 2022-01-06 |  | 2022-03-25 |  | 65%
| Integration and Testing | 2022-03-02 | 2022-06-27 | 2022-03-04 | 2022-07-22 | Will be Late | 0%
| Server, Gateway, Platform, and Database Setup | 2022-03-02 | 2022-03-25 | 2022-03-15 | 2022-04-27 | Will be Late | 0%
| Server and IoT Gateway Setup | [5 empty] | 0%
| Platform and Database Setup | [5 empty] | 0%
| Training Material and Documentation | 2022-03-02 | 2022-03-25 | 2022-03-04 | 2022-04-06 | Will be Late | 0%
| User Training | 2022-03-16 | 2022-04-08 | 2022-03-16 | 2022-04-08 | Will be Late | 0%
| User Acceptance Test | 2022-03-17 | 2022-07-25 | 2022-06-28 | 2022-07-27 | Will be Late | 0%
| Go Live Support | 2022-03-21 | 2022-07-30 | 2022-03-21 | 2022-08-02 | Will be Late | 0%
| ThingWorx Foundation Developer Training | 2022-03-21 | 2022-04-20 | 2022-03-24 | 2022-04-27 | Will be Late | 0%
Project Objectives/Coverage:
To integrate an asset to:
a. Machine Overview
b. Machine Status
c. Machine Alarm Status
d. Spindle Condition
Work Breakdown
1 | Asset Data Tapping
2 | Machine Database Configuration
3 | ThingWorx Condition Monitoring Module Configuration (refer to project objectives/coverage)
4 | Development and Integration Testing
5 | User Acceptance Test
Prerequistes and Assumptions:
1 | Data sources for this Project is only asset controller
2 | Virtual Machines/Server that host ThingWorx, Machine Database and Business Database exists at Collins Aerospace with licensed Microsoft SQL Server for Machine Database and PostgreSQL for Native Database
3 | System Architecture to be determined and selected during project by CAD-IT and Collins Aerospace
4 | OT and IT network to be configured by Collins Aerospace
5 | No new modules or work packages development
6 | No new screens development
7 | Machine images to be provided by Collins Aerospace
8 | Parameters/tags to be acquired are available in the controller and mapped to the respective mashups (exclude Real-Time Critical Parameter mashup)
9 | Data tapping schedule to be determined together by Collins Aerospace and CAD-IT
10 | Maximum number of tags that will be direct tapped are 25 tags per machine
11 | If needed, Mazak OEM support to be provisioned by Collins Aerospace
12 | Assets are Mazak with model 530-6X II and i700
Exclusions
1 | Excludes OT and IT network configuration
2 | Excludes asset retrofitting
3 | Excludes ThingWorx Analytics
Deliverables
1 | Condition Monitoring Module Configuration (refer to project objectives/coverage)

## LPPP2 op2
Collins Aerospace Indonesia Lighthouse Pilot Project Proposed Phase 2 High-Level Timeline V1.0
Date: |  | 2022-05-13
Task Name | Planned Start Date | Estimated Start Date | Planned End Date | Estimated End Date | Status | Progress | 2022-05-01 |  |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  | 2022-06-01
[7 empty] | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-05-31 | 2022-06-07 | 2022-06-14 | 2022-06-21 | 2022-06-28 | 2022-07-05 | 2022-07-12 | 2022-07-19 | 2022-07-26 | 2022-08-02 | 2022-08-09 | 2022-08-16 | 2022-08-23 | 2022-08-30 | 2022-09-06 | 2022-09-13 | 2022-09-20 | 2022-09-27 | 2022-10-04 | 2022-10-11 | 2022-10-18 | 2022-10-25 | 2022-11-01 | 2022-11-08 | 2022-11-15 | 2022-11-22 | 2022-11-29 | 2022-12-06 | 2022-12-13
[7 empty] | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 16 | WEEK 16 | WEEK 17 | WEEK 18 | WEEK 19 | WEEK 20 | WEEK 21 | WEEK 22 | WEEK 23 | WEEK 24 | WEEK 25 | WEEK 26 | WEEK 27 | WEEK 28 | WEEK 29 | WEEK 30 | WEEK 31 | WEEK 32 | WEEK 33
Lighthouse Pilot Project Proposed Phase 2 | 2021-11-03 | 2022-05-03 | 2022-03-24 | 2022-06-30 | Will be Late | 37.28%
Project Kick-Off | 2021-11-03 | 2022-05-03 | 2021-11-03 | 2022-05-03 | On-Track | 100%
Architecture and Solution Design | 2021-11-04 | 2022-05-04 | 2021-11-15 | 2022-05-10 | Late | 100%
Joint Specification | 2021-11-16 | 2022-05-11 | 2021-11-17 | 2022-05-13 | Late | 100%
Data Tapping | 2021-11-17 | 2022-05-16 | 2022-02-01 | 2022-06-16 | Will be Late | 25%
Controller Direct Data Tapping |  | 2022-01-27 |  | 2022-02-27 |  | 20%
Sensor Retrofitting | [5 empty] | 30%
Development | 2021-11-16 | 2022-05-16 | 2022-03-01 | 2022-07-15 | Will be Late | 83.33%
Project Baseline Development |  | 2021-12-14 |  | 2022-01-06 |  | 100%
Database Development |  | 2022-01-03 |  | 2022-01-14 |  | 85%
ThingWorx Work Packages |  | 2022-01-06 |  | 2022-03-25 |  | 65%
Development Testing | 2022-03-02 | 2022-07-18 | 2022-03-04 | 2022-07-23 | Will be Late | 0%
Server, Gateway, Platform, and Database Setup | 2022-03-02 | 2022-03-25 | 2022-03-15 | 2022-04-27 | Will be Late | 0%
Server and IoT Gateway Setup | [5 empty] | 0%
Platform and Database Setup | [5 empty] | 0%
Training Material and Documentation | 2022-03-02 | 2022-07-18 | 2022-03-04 | 2022-07-20 | Will be Late | 0%
User Training | 2022-03-16 | 2022-07-24 | 2022-03-16 | 2022-07-24 | Will be Late | 0%
User Acceptance Test | 2022-03-17 | 2022-07-26 | 2022-06-28 | 2022-07-27 | Will be Late | 0%
Go Live Support | 2022-03-21 | 2022-07-27 | 2022-03-21 | 2022-07-29 | Will be Late | 0%
ThingWorx Foundation Developer Training | 2022-03-21 | 2022-04-20 | 2022-03-24 | 2022-04-27 | Will be Late | 0%